## Sheet1
MAIN TRAIN PLANNED START | R/O | SITE REF NO. |  | POSTCODE | SURFACE DRESSING PROGRAMME 2024 |  |  | RESTRICTIONS
COMBI PLANNED START |  |  | ROAD NAME |  | AREA | EXTENTS | TRAFFIC MANAGEMENT
2024-04-20 | 1 | L52 | WETHERBY ROAD | LS17 8NE | ROUNDHAY | A6120 RING ROAD TO RED HALL LANE | Stop&go | 09:30-15:30
2024-04-20 | 2 | L54 | STANKS LANE SOUTH | LS14 5NS | STANKS | STANKS DRIVE TO BARWICK ROAD | Road Closure | 09:30-15:30
2024-04-20 | 3 | L55 | STANKS DRIVE | LS14 5PA | STANKS | STANKS LANE NORTH TO FAWDON DRIVE | Road Closure | SAT/SUN
2024-04-20 | 4 | L56 | BARWICK ROAD | LS15 8JF | STANKS | A6120 ROUNDABOUT TO SMEATON APPROACH | Stop&go | 09:30-15:30
2024-04-20 | 5 | L57 | EASTWOOD LANE | LS14 5HT | SWARCLIFFE | BARWICK ROAD TO SWARCLIFFE DRIVE | Road Closure | SAT/SUN
2024-04-20 | 6 | L58 | SWARCLIFFE DRIVE | LS14 5HT | SWARCLIFFE | EASTWOOD LANE TO STANKS LANE NORTH | Road Closure | SAT/SUN
2024-04-22 | 7 | L28 | GREEN LANE | WF3 3QH | LOFTHOUSE | CARLTON LANE TO OUZEWELL GREEN | Road Closure | 09:30-15:30
2024-04-22 | 8 | L29 | JUMBLES LANE | WF3 3RU | LOFTHOUSE | A61 LEEDS ROAD TO CARLTON LANE | Road Closure | 09:30-15:30
2024-04-25 | 9 | L50 | SPRINGHEAD ROAD | LS26 0EX | ROTHWELL | PARK LANE TO HAIGH ROAD | Road Closure | Unrestricted
2024-04-25 | 10 | L51 | WOOD LANE | LS26 0PW | ROTHWELL | HAIGHSIDE DRIVE TO A61 WAKEFIELD ROAD | Stop&go | 09:30-15:30
2024-04-25 | 11 | L44 | NORTH LANE | LS26 8NS | OULTON | HOLMSLEY FIELD LANE TO HOMSLEY LANE | Road Closure | 09:30-15:30
2024-04-25 | 12 | L64 | CHURCH STREET | LS26 8PQ | WOODLESFORD | HIGHFIELD LANE TO OULTON LANE | Road Closure | 09:30-15:30
2024-04-25 | 13 | L65 | HOLMSLEY LANE | LS26 8PQ | WOODLESFORD | NORTH LANE TO LEEDS ROAD | Road Closure | 09:30-15:30
2024-04-25 | 14 | L33 | ST GEORGES ROAD | LS10 4TQ | MIDDLETON | ZEBRA TO TOWCESTER AVE | Road Closure | 09:30-15:30
2024-04-26 | 15 | L61 | WESTERTON ROAD | WF3 1BB | TINGLEY | CONSTABLE ROAD TO SYKE ROAD | Road Closure | 09:30-15:30
2024-04-26 | 16 | L38 | BRUNTCLIFFE ROAD | LS27 0LQ | MORLEY | A643 BRUNTCLIFFE LANE TO SCOTCHMAN LANE | Stop&go | 09:30-15:30
2024-04-26 | 17 | L10 | BUSLINGTHORPE LANE | LS7 2AH | CHAPELTOWN | MEANWOOD ROAD TO SAVILLE MOUNT | Road Closure | 09:30-15:30
2024-04-26 | 18 | L9 | SAVILE MOUNT | LS7 2HR | CHAPELTOWN | CHAPLETOWN ROAD TO BUSLINGTHORPE LANE | Road Closure | Unrestricted
2024-04-27 | 19 | L23 | DOMESTIC ROAD | LS12 6HG | HOLBECK | GELDERD ROAD TO DOMESTIC STREET BOTH SIDES D/CWAY | Road Closure | 09:30-15:30
2024-04-27 | 20 | L1 | SELBY ROAD | LS15 9JA | AUSTHORPE | SAINSBURYS RDBT TO A6120/B6159 WHITKIRK RDBT | Lane Closures | 09:30-15:30
2024-04-27 | 21 | L34 | RING ROAD MOORTOWN | LS17 8PF | MOORTOWN | ROUNDHAY PARK LANE NEW BED TO NEW BED AFTER SHADWELL LANE | Stop&go / LANE CLOSURE | 09:30-15:30
2024-04-29 | 22 | L20 | ODDA LANE | LS20 8NZ | HAWKSWORTH | MAIN STREET TO HILLINGS LANE | Road Closure | Unrestricted
2024-04-29 | 23 | L21 | BINGLEY ROAD | BD16 3BJ | HAWKSWORTH | DIST BOUNDARY TO HILLINGS LANE | Road Closure | 09:30-15:30
2024-04-29 | 24 | L22 | HILLINGS LANE | LS20 8PE | HAWKSWORTH | OLD LANE TO BDRY J/O BINGLEY RD RHS | Road Closure | 09:30-15:30
2024-04-29 | 25 | L24 | BAYTON LANE | LS18 5EZ | HORSFORTH | 40 SIGN AT HOUSES TO LAYTON LANE | Road Closure | 09:30-15:30
2024-04-30 | 26 | L27 | HARROGATE ROAD | LS7 4QD | LEEDS | WOOD LANE TO KING LANE | Stop&go | 09:30-15:30
2024-04-30 | 27 | L14 | GLEDHOW VALLEY ROAD | LS8 4DP | GLEDHOW | ROUNDHAY RD TO ALLERTON GRANGE WAY | Road Closure | 09:30-15:30
2024-04-30 | 28 | L18 | HAREHILLS AVENUE | LS8 4HU | HAREHILLS | CHAPELTOWN ROAD TO ROUNDHAY ROAD | Road Closure | 09:30-15:30
2024-05-01 | 29 | L71 | CARR MANOR ROAD | LS17 5BQ | MOORTOWN | STAINBECK ROAD TO KING LANE | Road Closure | 09.30-15.30
2024-05-01 | 30 | L30 | STAINBECK ROAD | LS7 2QY | MEANWOOD | MEANWOOD ROAD TO STAINBECK LANE | Road Closure | 09:30-15:30
2024-05-01 | 31 | L7 | POTTERNEWTON LANE | LS7 2EG | CHAPEL ALLERTON | STAINBECK ROAD TO SCOTT HALL ROAD | Road Closure | 09:30-15:30
2024-05-01 | 32 | L70 | THE AVENUE | LS17 7BD | ALWOODLEY | KING LANE TO ALWOODLEY LANE | Road Closure | 09.30-15.30
2024-05-01 | 33 | L31 | MONK BRIDGE ROAD | LS6 4DX | MEANWOOD | MOOR ROAD TO MEANWOOD ROAD | Road Closure | 09:30-15:30
2024-05-02 | 34 | L11 | GREEN LANE | LS16 7LW | COOKRIDGE | COOKRIDGE LANE TO WOODHILL ROAD | Road Closure | 09:30 - 15:30
2024-05-18 | 35 | L43 | POOL ROAD | LS21 1FD | OTLEY | EAST BUSK LANE TO MAIN STREET A658 SLIP | Stop&go | 09:30-15:30
2024-05-19 | 36 | L40 | WESTGATE | LS21 3DT | OTLEY | ILKLEY ROAD TO KIRKGATE | Road Closure | SUNDAY
2024-05-19 | 37 | L41 | PIPER LANE | LS21 3JU | OTLEY | WEST CHEVIN RD TO ILKLEY RD | Road Closure | SUNDAY
2024-05-19 | 38 | L42 | BRADFORD ROAD | LS21 3JT | OTLEY | A660 OTLEY RD RDBT TO WEST CHEVIN RD | Road Closure | SUNDAY
2024-05-19 | 39 | L59 | BRADFORD ROAD | LS28 6QB | STANNINGLEY | DAWSONS CORNER R@ TO WEST GROVE STREET | Stop&go | SUNDAY
2024-05-19 | 40 | L60 | STANNINGLEY BYPASS | LS28 6AB | STANNINGLEY | OWL COTES SLIP BOTH SIDES OF BYPASS | Road Closure | EARLY SUNDAY
2024-05-19 | 41 | L6 | KIRKSTALL ROAD | LS4 2AG | BURLEY | WILLOW ROAD TO WELLINGTON BRIDGE STREET - INBOUND ONLY | Lane Closures | SUNDAY
2024-05-19 | 42 | L67 | LIDGETT LANE | LS25 1LL | GARFORTH | CHURCH LANE TO A63 SELBY ROAD | Road Closure | SUNDAY
2024-06-06 | 43 | L48 | STATION STREET | LS28 8PR | PUDSEY | CARLISLE ROAD TO GREENSIDE | Road Closure | Unrestricted
2024-06-06 | 44 | L47 | RADCLIFFE LANE | LS28 7EU | PUDSEY | CHURCH LANE TO ROBIN LANE | Road Closure | 09:30-15:30
2024-06-06 | 45 | L12 | NEW LANE | BD11 1NH | DRIGHLINGTON | GILDERSOME LANE TO WHITEHALL ROAD | Road Closure | Unrestricted
2024-06-07 | 46 | L39 | BIRDCAGE WALK | LS21 3JQ | OTLEY | WEST CHEVIN RD TO THE OLD VICAGE , SD BED END | Road Closure | Unrestricted
2024-06-07 | 47 | L66 | GREEN LANE | LS19 7BY | YEADON | A65 RDBT TO HOUSE NO 19 - 21 | Road Closure | 09:30-15:30
2024-06-10 | 48 | L35 | COMMERCIAL STREET | LS27 8AG | MORLEY | ALBION STREET TO PEEL STREET | Road Closure | 09:30-15:30
2024-06-10 | 49 | L36 | FOUNTAIN STREET | LS27 9AE | MORLEY | CHARTIST WAY RDBT TO COMMERCIAL ST | Road Closure | 09:30-15:30
2024-06-10 | 50 | L13 | MOOR KNOLL LANE | WF3 2DX | EAST ARDSLEY | MAIN STREET TO COMMON LANE | Road Closure | 09:30-15:30
2024-06-11 | 51 | L2 | EAST GRANGE RISE | LS10 3ED | BELLE ISLE | MIDDLETON ROAD TO LOW GRANGE CRESCENT | Road Closure | Unrestricted
2024-06-11 | 52 | L3 | EAST GRANGE ROAD | LS10 3EG | BELLE ISLE | BELLE ISLE ROAD TO EAST GRANGE RISE | Road Closure | Unrestricted
2024-06-11 | 53 | L4 | LOW GRANGE CRESCENT | LS10 3EB | BELLE ISLE | BELLE ISLE ROAD TO EAST GRANGE RISE | Road Closure | Unrestricted
2024-06-11 | 54 | L32 | MANOR FARM DRIVE | LS10 3RE | MIDDLETON | NEWHALL ROAD TO END | Road Closure | Unrestricted
2024-06-12 | 55 | L8 | SPENCER PLACE | LS7 4DU | CHAPELTOWN | HAREHILLS AVENUE TO ROUNDHAY ROAD | Road Closure | 09:30-15:30
2024-06-12 | 56 | L62 | LATCHMERE DRIVE | LS16 5DY | WEST PARK | FILLINGFIR DRIVE TO OLD FARM APPROACH | Road Closure | Unrestricted